## Workplan
Project Workplan
Please complete the table below, ensuring that the implementation period does not exceed 24 months. An example is provided in italics for your reference (please delete this).
Once you have completed this table, please proceed to the next tab (project budget).
Project Outputs (add/delete as necessary) | Indicators | Activities | Timeline (Year 1) |  |  |  | Timeline (Year 2) (if applicable)
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Note: only include activities to be supported by Youth4Climate here.
Project Output 1: 50 youth trained in sustainable practices of Mbogo community tree planting(organic farming, waste management ) | Baseline: Numberof youth trained in sustainable practices 0. Target: 50. Means of verification: Training attendance records, Certificates issued | Organize 3 training workshops on sustainable practices of planting trees in Mbogo community( organic farming, waste management) | bar: Timeline (Year 1) Q1 to Timeline (Year 1) Q3
Invite 2 experts for hand on training sessions in Mbogo community | bar: Timeline (Year 1) Q1 to Timeline (Year 1) Q3
Provide training materials and certificates to participants of Mbogo community | bar: Timeline (Year 1) Q2 to Timeline (Year 1) Q4
Project Output 2: 10 green businesses launched and operational supporting Mbogo community tree planting | Baseline:Number of green business launched 0 Target: 10 Means of verification Business registration documents, Photos of businesses, Operational reports | Provide funding for Mbogo community 10 green business ideas | bar: Timeline (Year 1) Q2 to Timeline (Year 1) Q3
Offer mentorship and couching to selected Mbogo entrepreneurs | bar: Timeline (Year 1) Q2 to Timeline (Year 2) (if applicable) Q1
Facilitate networking events for green business owners | bar: Timeline (Year 1) Q3 to Timeline (Year 1) Q4
Project Output 3: 1000 trees planted and maintained in Mbogo community | Baseline: Trees planted and maintained 0 Target: 1000 Means of verification: Means of verification: Planting records, Photos of planting events, Quarterly monitoring reports | Source and distribute 1000 tree seedlings in Mbogo community( native species) | bar: Timeline (Year 1) Q1 to Timeline (Year 1) Q2
Organize Mbogo community planting events (2 days) | bar: Timeline (Year 1) Q2 to Timeline (Year 1) Q3
Esterblish a tree nursery for Mbogo future replanting efforts | bar: Timeline (Year 1) Q2 to Timeline (Year 1) Q4
Project Output 4: Community composting system established supporting tree planting efforts, processing 500 kg organic waste/month | Baseline: Organic waste composited (0kg/month) Target: 500 kg/month. Meansof verification Composting records, Photos of composting site, Waste collection logs | Set up Mbogo community composting infrastructure (bins, tools) | bar: Timeline (Year 1) Q1 to Timeline (Year 1) Q2
Train 20 Mbogo community members on composting techniques | bar: Timeline (Year 1) Q2 to Timeline (Year 1) Q4
Establish organic waste collection system in Mbogo village | bar: Timeline (Year 1) Q2 to Timeline (Year 1) Q3
By implementing these measures, Mbogo Zone's tree planting initiatives will effectively enhance environmental resilience and community livelihoods in Kitwekyambogo Ward, Luuka Town Council, Luuka District, Uganda.

## Budget
Project Budget (USD)
Important Note: The implementation period cannot exceed 24 months - the budget timeline can be adjusted based on the actual implementation timeline. The budget must be provided in US Dollars.
Proposals with budgets in other currencies or exceeding the maximum of USD 30,000 (for the portion requested from Youth4Climate) will be disqualified.
If other sources of funding are referenced in the budget, please make sure it is clear which part of the budget would be covered by Youth4Climate and which part would be covered through co-financing.
You may be asked to provide evidence of any sources of co-funding referenced in your budget or proposal.
The proposed budget cannot be changed following submissions. All possible costs should be considered as part of the submitted budget, such as taxes and customs fees.
| Outputs* | Description** | Cost per unit | total number of units | Q1 | Q2 | Q3 | Q4 | Q1 (Year 2) | Q2 | Q3 | Q4 | Total (USD) | Comments - please add any necessary clarification (e.g. travel to-from etc.) For equipment please provide as exact a description for each type of item to be purchased.
| Output 1: 50 youth trained in Mbogo sustainable practice of planting tree species (Year 1 & 2) - Contractual Services: $4,000 (2 experts, 4 workshops, Q1-Q4, Y1-Y2) - Equipment: $1,500 (training materials, certificates, Q2, Y1-Y2) - Local Transportation: $500 (transport for experts, Q1-Q2, Y1) | Project-related travel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contractual Services | 1000 | 2 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 4000 | 2 experts, 4 workshops
|  | Staff salaries |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications & Knowledge Management |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equipment | 750 | 2 | 0 | 1000 | 0 | 0 | 500 | 0 | 0 | 0 | 1500 | Refreshment, Comfortable seating and desks, projector/ screen for presentations, white board/flip charts, note book and work books, pendant pencils, clip boards for participants, printed handouts
|  | Local Transportation | 250 | 2 | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | Transport for experts
|  | Shipping Costs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rental costs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other (Please specify) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTALS OUTPUT 1 |  | 2000 | 6 | 1250 | 2250 | 1000 | 1000 | 500 | 0 | 0 | 0 | 6000
| Output 2: 10 green businesses launched supporting Mbogo community tree planting(Year 1 & 2) - Other (Funding for green businesses): $10,000 (grants, Q2-Q3, Y1-Y2) - Contractual Services: $2,000 (mentorship, Q2-Q4, Y1-Y2) - Local Transportation: $500 (networking events, Q3, Y1) | Project-related travel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contractual Services | 1000 | 2 | 0 | 1000 | 500 | 500 | 0 | 0 | 0 | 0 | 2000 | Mentorship
|  | Staff salaries |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications & Knowledge Management |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equipment |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Local Transportation | 500 | 1 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500
|  | Shipping Costs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rental costs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other ( Funding Mbogo Green businesses) specifically: -Environmental conservation: Mbogo Tree planting, reforestation, and sustainable land management. - Sustainable agriculture: Mbogo Agroforestry practices that integrate trees into farming. - Eco-education: Mbogo Workshops and training on sustainable practices. These initiatives support environmental resilience and community development. | 1000 | 10 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 10000
| TOTALS OUTPUT 2 |  | 2500 | 13 | 0 | 6000 | 1000 | 500 | 5000 | 0 | 0 | 0 | 12500
| Output 3: 1000 trees planted in Mbogo (Year 1 & 2) - Equipment: $2,000 (seedlings, tools, Q1-Q2, Y1-Y2) - Local Transportation: $500 (planting events, Q2, Y1-Y2) - Other (Nursery setup): $1,000 (Q2-Q3, Y1) | Project-related travel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contractual Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Staff salaries |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications & Knowledge Management |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equipment( seedlings, tools) | 1000 | 2 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | - Shovels - Spades - Trowels - Pruning shears - Watering cans - Seedling trays - Transplanting tubes or pots - Wheelbarrow - Gloves - Spray pump - Record books - Gumboots
|  | Local Transportation | 250 | 2 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500
|  | Shipping Costs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rental costs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other (Please specify) | 500 | 1 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 1000
| TOTALS OUTPUT 3 |  | 1750 | 5 | 1000 | 2000 | 500 | 0 | 0 | 0 | 0 | 0 | 3500
| Output 4: Mbogo Community composting system supporting tree planting efforts - Equipment: $2,000 (bins, tools, Q1-Q2, Y1) - Contractual Services: $1,000 (training, Q2-Q3, Y1) - Local Transportation: $500 (setup, Q2, Y1) | Project-related travel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contractual Services | 500 | 2 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 1000 | Training
|  | Staff salaries |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications & Knowledge Management |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equipment | 1000 | 2 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -Shovels, forks, and wheelbarrows - Compost turners or aerators - Thermometers (to monitor temperature) - pH meters (to check soil acidity) - Sieves or screens (to sift compost) - Buckets or bins (for collecting organic waste)
|  | Local Transportation | 500 | 1 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500
|  | Shipping Costs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rental costs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other (Please specify) |  |  | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0
| TOTALS OUTPUT 4 |  | 2000 | 5 | 1000 | 2000 | 500 | 0 | 0 | 0 | 0 | 0 | 3500
| GRAND TOTALS (USD) |  |  |  | 3250 | 12250 | 2000 | 1500 | 5500 | 0 | 0 | 0 | 24500
By implementing these measures, Mbogo Zone's tree planting initiatives will effectively enhance environmental resilience and community livelihoods in Kitwekyambogo Ward, Luuka Town Council, Luuka District, Uganda.
| *Please add Outputs as appropriate in line with your proposal | ** Please use , modify or add fields as appropriate, if field is not needed, please delete. Note that the following types of expenditures will not be considered eligible:
Overhead costs not directly related to the implementation of the project;
Interest or debt owed to any third party;
Expenditures and provisions for possible future losses or debts;
Items already financed through another similar scheme, program or institution, financial awards;
Bank and currency exchange expenses, losses, fees and penalties.

## Sheet2 (hidden)
Home-based Expertise
Yes
Mostly
No